## RTM
Requirement Traceability Matrix (RTM)
X = test case covers the requirement
Prepared by:- Anushka Sakare
Req ID | Requirement | TC_01 | TC_02 | TC_03 | TC_04 | TC_05 | TC_06 | TC_07 | TC_08 | TC_09 | TC_10 | Total TCs | Linked Defects
REQ_01 | User Registration | [10 empty] | 1 | BUG-003 | bar: TC_01
REQ_02 | Login and Logout | [10 empty] | 1 | - | bar: TC_01
REQ_03 | Product Search and Product Details | [10 empty] | 1 | BUG-005 | bar: TC_02
REQ_04 | Wishlist Management | [10 empty] | 2 | - | bar: TC_02; TC_09
REQ_05 | Product Comparison | [10 empty] | 1 | - | bar: TC_03
REQ_06 | Shopping Cart | [10 empty] | 4 | BUG-004 | bar: TC_04 to TC_05; TC_09 to TC_10
REQ_07 | Checkout Process | [10 empty] | 4 | BUG-001, BUG-002 | bar: TC_05; TC_07 to TC_09
REQ_08 | Customer Information Management | [10 empty] | 1 | - | bar: TC_06
REQ_09 | Address Management | [10 empty] | 1 | BUG-001, BUG-002 | bar: TC_07
REQ_10 | Order Confirmation and Order History | [10 empty] | 1 | - | bar: TC_08
REQ_11 | Category Browsing | [10 empty] | 1 | - | bar: TC_10
Total | Requirements per test case | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 18

## Test Case Status
TC ID | Test Scenario | Requirements Covered | Execution Status | Defect ID | Remarks
TC_01 | Verify new user registration, login, browsing and logout | REQ_01, REQ_02 | Fail | BUG-003 | Defect logged in Bug Report
TC_02 | Verify login, product search, product details, add to wishlist and wishlist verification | REQ_03, REQ_04 | Fail | BUG-005 | Defect logged in Bug Report
TC_03 | Verify login, product comparison and comparison verification | REQ_05 | Pass | -
TC_04 | Verify login, add product to cart, update quantity, remove product and cart verification | REQ_06 | Fail | BUG-004 | Defect logged in Bug Report
TC_05 | Verify login, adding multiple products, cart changes and checkout | REQ_06, REQ_07 | Pass | -
TC_06 | Verify login, managing customer information, saving changes and verifying saved data | REQ_08 | Pass | -
TC_07 | Verify login, adding address, selecting product, checkout and address verification | REQ_07, REQ_09 | Fail | BUG-001, BUG-002 | Defect logged in Bug Report
TC_08 | Verify login, product purchase, order confirmation and order history | REQ_07, REQ_10 | Pass | -
TC_09 | Verify login, wishlist product moved to cart and checkout | REQ_04, REQ_06, REQ_07 | Pass | -
TC_10 | Verify login, category browsing, product selection, add to cart, continue shopping and final cart verification | REQ_06, REQ_11 | Pass | -

## Summary
RTM Summary
Total requirements | 11
Total test cases | 10
Requirements with at least one test case | 11
Requirement coverage (%) | 100%
Test cases passed | 6
Test cases failed | 4
Pass percentage | 60%