## Bug Report
Bug ID | Module | Bug Title | Steps to Reproduce | Expected Result | Actual Result (Sample) | Severity | Priority | Status | Browser | Operating System | Testing Type
BUG_001 | Login | Login accepts invalid password | Enter valid registered email and incorrect password; click Login. | System should reject login and display an appropriate error message. | Sample result: login is accepted despite incorrect password. | Critical | High | Open | Chrome | Windows 11 | Functional
BUG_002 | Registration | Registration accepts invalid email format | Enter an invalid email such as abc@, complete other required fields, and click Register. | System should reject the email and display an email validation message. | Sample result: registration is completed with an invalid email address. | Major | High | Open | Chrome | Windows 11 | Functional
BUG_003 | Product | Add to Cart button does not add selected product | Open a product page, click Add to Cart, and navigate to the cart. | Selected product should appear in the shopping cart. | Sample result: selected product does not appear in the cart. | Major | High | Open | Chrome | Windows 11 | Functional
BUG_004 | Shopping Cart | Cart displays incorrect product quantity | Add one product, increase its quantity to 2, and inspect the cart. | Cart should display the updated quantity as 2. | Sample result: cart continues to display quantity as 1. | Major | High | Open | Chrome | Windows 11 | Functional
BUG_005 | Product Search | Search displays irrelevant products | Search for a specific product name and review the results. | Results should match the entered search keyword. | Sample result: unrelated products are displayed. | Minor | Medium | Open | Chrome | Windows 11 | Functional
BUG_006 | Checkout | Checkout proceeds without selecting a delivery address | Add a product, open checkout, leave the address unselected, and click Continue. | System should prevent progression and request a delivery address. | Sample result: user is allowed to proceed without selecting an address. | Critical | High | Open | Chrome | Windows 11 | Functional
BUG_007 | Login | Password is visible instead of masked by default | Open the login page, enter a password, and inspect the password field. | Password characters should be masked by default. | Sample result: password characters are displayed in plain text. | Major | Medium | Open | Chrome | Windows 11 | Functional / Security
BUG_008 | Registration | Registration accepts empty mandatory fields | Open registration, leave mandatory fields empty, and click Register. | System should block submission and display required-field validation messages. | Sample result: registration is accepted without mandatory information. | Major | High | Open | Chrome | Windows 11 | Functional
BUG_009 | Shopping Cart | Cart total does not update after removing a product | Add two products, note the total, remove one product, and inspect the total. | Cart total should be recalculated after the product is removed. | Sample result: previous total remains displayed. | Major | High | Open | Chrome | Windows 11 | Functional
BUG_010 | Login | No error message is displayed for invalid login credentials | Enter invalid login credentials and click Login. | System should display a clear and helpful error message. | Sample result: login fails but no error message is displayed. | Minor | Medium | Open | Chrome | Windows 11 | Functional

## Project Info
Field | Details
Project Name | E-Commerce Web Application
Application Type | Web Application
Testing Type | Functional Testing
Test Environment | Chrome Browser / Windows 11 (sample environment)
Document Purpose | Portfolio sample documenting defect reporting practices
Important Note | All defects and actual results are illustrative examples, not verified defects from a live application. Update them after executing tests.